## Slide 1
GMAT Question Generation via AI Fine-Tuning
Strategic Proposal for UpToTen Test Platform

## Slide 2
The Challenge: Question Gap Analysis
1,342
Current Questions Available
1,172
Questions Needed Per Student/Cycle
5,000+
Additional Questions Needed for Scale
4 weeks
Target Timeline to Fill Gap

## Slide 3
Current Question Distribution
Section | Available | Per Cycle Need | Status
Quantitative Reasoning | 582 | 469 | ✓ 1 cycle
Verbal Reasoning | 383 | 311 | ✓ 1 cycle
Data Insights | 377 | 392 | ⚠ Slight gap
TOTAL | 1,342 | 1,172 | Gap grows with scale

## Slide 4
The Proposed Solution

## Slide 5
What is AI Fine-Tuning?
• Adapts a pre-trained AI model (GPT-4o) to your specific use case
• Trains on examples of desired output format and style
• Unlike prompting, it modifies the model's behavior permanently
• Result: Consistent, high-quality GMAT-style questions on demand
• One-time training → Unlimited generation capability

## Slide 6
Why Fine-Tuning?
Fine-Tuning Approach
• Low cost: ~$50 for training + generation
• High consistency: Same format every time
• Scalable: Generate thousands on demand
• Fast after setup: Seconds per question
• Token-efficient: No examples needed in prompts
Alternatives
• Manual creation: $25,000+ for 2,500 questions
• Few-shot prompting: Higher per-question cost
• Purchase questions: $5,000-15,000 licensing
• Partner with test prep: Revenue share + dependency
• All alternatives: Slower or more expensive

## Slide 7
How It Works: The Pipeline
• STEP 1: Select 150-300 of our best existing questions for training
• STEP 2: Convert to OpenAI's JSONL training format
• STEP 3: Fine-tune GPT-4o model (2-4 hours, ~$10)
• STEP 4: Generate new questions via API (~$8 per 1,000)
• STEP 5: Expert review and validation (in-house GMAT experts)
• STEP 6: Import approved questions to platform

## Slide 8
Implementation Plan

## Slide 9
4-Week Implementation Timeline
Week 1
• Select 150 training questions
• Build export scripts
• Set up OpenAI API
• Run first fine-tuning
• Generate 50 pilot questions
Week 2
• Expert reviews pilot
• Iterate on training
• Generate batch 1 (500)
• Begin parallel review
• Quality assessment
Week 3
• Scale generation (2,000+)
• Parallel expert review
• Fix/reject as needed
• Quality tracking
• Refinement cycle
Week 4
• Convert to platform format
• Database import
• Platform testing
• Final QA
• Launch!

## Slide 10
Cost Analysis
~$50
AI Costs (Training + Generation)
65 hrs
Total Human Effort (Dev + Expert)
$3,500
Total Estimated Cost (at $50/hour)
86%
Cost Savings vs. Manual Creation

## Slide 11
Cost Comparison: AI vs. Alternatives
Approach | Questions | Time | Cost
Manual Creation | 2,500 | 500+ hours | $25,000+
Purchase/License | 2,500 | 2-4 weeks | $5,000-15,000
AI + Expert Review | 2,500 | 65 hours | ~$3,500
SAVINGS with AI | — | 87% less time | 86% less cost

## Slide 12
Quality Assurance

## Slide 13
Quality Assurance Process
Automated Checks
• Format validation: Correct JSON structure
• Field verification: All required fields present
• Answer options: Exactly 5 choices (a-e)
• Mathematical validation: Verify calculations
• Duplication check: Compare to existing questions
Expert Review
• Mathematical/logical correctness
• Clear, unambiguous wording
• Appropriate difficulty level
• Realistic GMAT-style scenarios
• Quality explanation verification
• Target: 100-150 questions/expert/day

## Slide 14
Success Metrics & Go/No-Go Criteria
• QUALITY: >80% of generated questions pass expert review on first pass
• ACCURACY: <5% of questions contain mathematical/logical errors
• SPEED: 2,500+ validated questions delivered within 4 weeks
• COVERAGE: Balanced distribution across all topics and difficulty levels
•
• GO/NO-GO CHECKPOINTS:
• Day 5: Pilot review - >70% pass rate to continue
• Week 2: <10% error rate to scale up
• Week 4: 2,000+ validated questions to launch

## Slide 15
Risk Assessment

## Slide 16
Risk Assessment & Mitigations
Risk | Impact | Mitigation | Residual
Quality Issues | High | 100% expert review, pilot first | Low
Copyright/Legal | Medium | Train on format, not content; legal review | Low-Med
Difficulty Calibration | Medium | Include labels, track performance | Low
Timeline Slippage | Low | Buffer in schedule, parallel work | Low

## Slide 17
Decision & Next Steps

## Slide 18
Resources Required
• BUDGET:
• • ~$50 for AI costs (training + generation)
• • Expert time: 25-35 hours over 4 weeks
• • Developer time: 20-30 hours over 4 weeks
•
• PERSONNEL:
• • 1 Developer (scripts, integration, automation)
• • 1-2 GMAT Experts (training selection, validation)
•
• TECHNICAL:
• • OpenAI API account with payment method
• • Access to existing question database

## Slide 19
Deliverables
• JSONL export script - Convert existing questions to training format
• Fine-tuned GPT-4o model - Specialized for GMAT question generation
• Generation scripts - Automated question creation with validation
• Expert review system - Tracking spreadsheet for QA process
• 2,500+ validated questions - Imported and ready in platform
• Process documentation - Guide for future question generation

## Slide 20
Recommendation: Proceed
AI Fine-Tuning offers the best balance of speed, cost, and quality
✓ Fill the 5,000+ question gap in just 4 weeks
✓ Save 86% compared to manual creation
✓ In-house experts ensure quality control
✓ Scalable solution for future growth
✓ Low-risk pilot approach (50 questions first)

## Slide 21
Questions?
Ready to discuss next steps